## Sheet1
Pillar (optional) | CDL | BOM Analysis completion Date | NF Start Date | NF End Date | sent sample for revi Priya review
CX - CPQ | Shivam | Complete | 2026-10-05 | 2026-10-13 | Y / approved |  |  | SCM | Cal is final
CX - Sales | Vendor Xtentics | Complete | 2026-10-06 | 2026-10-14 | N/A
CX - Service | Phil | complete - 12 Oct | 2026-10-13 | TBD
SCM | farell | 2026-10-14 | 2026-10-15 | 2026-10-23
SCM | Nick | 2026-10-08 | 2026-10-09 | 2026-10-23 | < Tool update is pending - dates >
SCM | david | 2026-10-07 | 2026-10-08 | 2026-10-28 |  | ruchika to update dates | out of office
SCM | krithika | 2026-10-08 | 2026-10-09 | 2026-10-28
SCM | omkar | complete | 2026-10-08 | 2026-10-28
PRC | ashik | 2026-10-08 | 2026-10-12 | 2026-10-30
ERP | PANKAJ | 12-Oct -0 need to reaccess , this will be done on 14-Oct | 2026-10-14 | 2026-10-23
ERP | deepak | complete | 2026-10-08 | 2026-10-19
ERP | marcelina | 2026-10-14 | 2026-10-15 | 2026-10-23
ERP | chris | 2026-10-08 | 2026-10-12 | 2026-10-15
ERP | richard | 2026-10-08 | 2026-10-09 | 2026-10-16 |  | (?)
ERP | barney | complete | 2026-10-09 | 2026-10-16
HCM | Deb | complete | 2026-10-07 | 2026-10-23 | Y / approved
HCM | Jess | complete | 2026-10-06 | 2026-10-20
HCM | Kurt | complete | 2026-10-23 | 2026-10-23
HCM | Nigel | complete | 2026-10-06 | 2026-10-23
HCM | Rohit | complete | 2026-10-07 | 2026-10-15
HCM | Sarah | complete | 2026-10-20 | 2026-10-22

## Sheet2
Report Issue Day : Start Monday
We should ensure that the end date is not incorrect in sharepoint
Formal email to CDL manager - to ask for end date confirmation for all CDLs
This is to prevent discrepancy in dates
This is also to ensure the number of feature matches with their end date count
Let , we as OUPMs review a couple of videos of each CDL , so that when we meet Priya on Monday , we will have an idea how the CDL has recordewd . We shall place our observation across to priya .
Reminder to complete the setup information in sharepoint as of today