## HCM
| 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
CDL | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02
Jess | KPMG AI Agent Cert Prep Training Delivery Onsite | 26C NF | 26C NF AIAS AG Test (4 days) | Travel: Austin Partner Event: AI Agent Studio | 26C NF Design Doc: AIAS 26C | Content Dev: AIAS 26C | Content Dev: AIAS 26C | Record: AIAS 26C | Record: AIAS 26C | Holiday US | Record: Fast Formula
| KPMG AI Agent Cert Prep Training Delivery Onsite | KPMG AI Agent Cert Prep Training Delivery Onsite | 26C NF AIAS AG Test (4 days) | Inperson: Austin Partner Event: AI Agent Studio | 26C NF Design Doc: AIAS 26C | Content Dev: AIAS 26C | Content Dev: AIAS 26C | Record: AIAS 26C | Partner Session Prep | Record: AIAS 26C | Record: Fast Formula
| 26C NF | KPMG AI Agent Cert Prep Training Delivery Onsite | 26C NF AIAS AG Test (4 days) | Inperson: Austin Partner Event: AI Agent Studio | Live Session Prep Day | Content Dev: AIAS 26C | Content Dev: AIAS 26C | Record: AIAS 26C | Partner Session Prep | Record: AIAS 26C | Record: Fast Formula
| 26C NF | KPMG AI Agent Cert Prep Training Delivery Onsite | 26C NF AIAS Partner Training VT | Inperson: Austin Partner Event: AI Agent Studio | Live Session: Inside the AI Agent Studio | Content Dev: AIAS 26C | Content Dev: AIAS 26C | Record: AIAS 26C | HOLD eOPN Partner Event (Ruchika POC) | Record: AIAS 26C | 26D BOM Update
| 26C NF | 26C NF AIAS AG Test (4 days) | AIAS Partner Training VT 26C NF | Navigator July Release OOO | Design Doc: AIAS 26C | Content Dev: AIAS 26C | Content Dev: AIAS 26C | Record: AIAS 26C | Record: AIAS 26C | Record: AIAS 26C | 26D BOM Update
Nigel | 26C NF | 26C NF | Portfolio Review Meeting Prep | Navigator July Release | Design Doc: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Develop: Oracle Fusion Cloud HCM: Succession Management and Talent Review | Record: Oracle Fusion Cloud HCM: Succession Management and Talent Review | Holiday UK | Content Dev: Oracle Fusion Cloud HCM: Career Development | Content Dev: Oracle Fusion Cloud HCM: Career Development | Record: Oracle Fusion Cloud HCM: Career Development | Record: Oracle Fusion Cloud HCM: Career Development
| AM: 26C NF PM: eOPN Partner Event (Ruchika POC) Elevate your OTBI and BIP Reporting | 26C NF | Portfolio Review Meeting Prep | Record: Oracle Fusion Cloud HCM: Configure Goal and Performance Management (+AI) | Design Doc: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Develop: Oracle Fusion Cloud HCM: Succession Management and Talent Review | Record: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Content Dev: Oracle Fusion Cloud HCM: Career Development | Content Dev: Oracle Fusion Cloud HCM: Career Development | Record: Oracle Fusion Cloud HCM: Career Development | Record: Oracle Fusion Cloud HCM: Career Development
| 26C NF | 26C NF | 26C NF (45 NF identified for development) Portfolio Review Meeting | Record: Oracle Fusion Cloud HCM: Configure Goal and Performance Management (+AI) | OOO | OOO | OOO | Record: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Content Dev: Oracle Fusion Cloud HCM: Career Development |  | Record: Oracle Fusion Cloud HCM: Career Development | Record: Oracle Fusion Cloud HCM: Career Development
| 26C NF | 26C NF | 26C NF | Record: Oracle Fusion Cloud HCM: Configure Goal and Performance Management (+AI) | Design Doc: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Develop: Oracle Fusion Cloud HCM: Succession Management and Talent Review | Record: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Content Dev: Oracle Fusion Cloud HCM: Career Development | 26D BOM Update | Record: Oracle Fusion Cloud HCM: Career Development
| 26C NF | 26C NF | 26C NF | Record: Oracle Fusion Cloud HCM: Configure Goal and Performance Management (+AI) | Design Doc: Oracle Fusion Cloud HCM: Succession Management and Talent Review | OOO | Develop: Oracle Fusion Cloud HCM: Succession Management and Talent Review | Design Doc: Oracle Fusion Cloud HCM: Career Development | OOO | Content Dev: Oracle Fusion Cloud HCM: Career Development | 26D BOM Update | Record: Oracle Fusion Cloud HCM: Career Development | OOO
Sarah | 26C NF | 26C NF | 26C NF (35 features; 3 features per day; 12 days) CLS Live 1hr Prep: Interview Scheduling in Recruiting | Navigator July Release | Content Dev: Recruiting Booster Course | Record: Recruiting Booster Course | Develop: Opportunity Marketplace Agentic App 26C | Record: Opportunity Marketplace Agentic App 26C |  | Holiday US
| 26C NF | 26C NF | 26C NF (35 features; 3 features per day; 12 days) CLS Live 1 hr Delivery: Interview Scheduling in Recruiting | Record: Applied Learning Fusion Recruting Implementation Project 26C | Design Doc: Recruting Imp 26C | Record: Recruiting Imp 26C | Develop: Opportunity Marketplace Agentic App 26C | Record: Opportunity Marketplace Agentic App 26C
| 26C NF | 26C NF | 26C NF | Record: Applied Learning Fusion Recruting Implementation Project 26C | Design Doc: Recruting Imp 26C | Record: Recruiting Imp 26C | Develop: Opportunity Marketplace Agentic App 26C
| 26C NF | 26C NF | 26C NF | Design Doc: Recruiting Booster Course | Record: Recruiting Booster Course | Record: Recruiting Imp 26C | Develop: Opportunity Marketplace Agentic App 26C |  |  |  | 26D BOM Update
| 26C NF | 26C NF | 26C NF | Content Dev: Recruiting Booster Course | Record: Recruiting Booster Course | Design Doc: Opportunity Marketplace Agentic App 26C |  |  |  |  | 26D BOM Update
Kurt | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: 26C NF; 2026-07-27: 26C NF; 2026-09-07: Holiday US
| 26C NF | 26C NF | 26C NF | Navigator July Release | [5 empty] | OOO
| 26C NF | 26C NF | 26C NF | [6 empty] | OOO
| 26C NF | 26C NF | 26C NF | [6 empty] | OOO | 26D BOM Update
| 26C NF | 26C NF | 26C NF |  |  | OOO |  |  |  | OOO | 26D BOM Update
Deb | 26C NF | 26C NF | Jury Duty | Develop: Benefits Imp 26C | OOO | Live Session Prep Day | OOO | Develop: Journeys Imp 26C | Record: Benefits Imp 26C | Holiday US | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C
| 26C NF | 26C NF | Develop: Benefits Imp 26C | Develop: Journeys Imp 26C | OOO | August Live Session | OOO | Develop: Journeys Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C
| 26C NF | 26C NF | Develop: Benefits Imp 26C | Develop: Journeys Imp 26C | OOO | Develop: Journeys Imp 26C | OOO | Develop: Journeys Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C | Record: Benefits Imp 26C
| 26C NF | 26C NF | Develop: Benefits Imp 26C | Develop: Journeys Imp 26C | OOO | Develop: Journeys Imp 26C | OOO | Record: Benefits Imp 26C | Record: Benefits Imp 26C | OOO | 26D BOM Update | Record: Benefits Imp 26C
| 26C NF | 26C NF | Develop: Benefits Imp 26C | Develop: Journeys Imp 26C | OOO | OOO | OOO | Record: Benefits Imp 26C | Record: Benefits Imp 26C | OOO | 26D BOM Update | Record: Benefits Imp 26C
Susan | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: 26C NF; 2026-09-07: Holiday US
| 26C NF | 26C NF | 26C NF
| 26C NF | 26C NF | 26C NF
| 26C NF | 26C NF | 26C NF
| 26C NF | 26C NF | 26C NF
Rohit | 26C NF | 26C NF | 26C NF VT- Testing Agent Studio Labs (26C) | AI Agent Studio What's new video recording | 26C NF | Re-do AI Agents/Studio in Using GHR | Retrofit: AI Agents/Studio in Using GHR: Record | Oracle Fusion Cloud HCM: Workflows and Approvals: DD | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev | Oracle Fusion Cloud HCM: Workflows and Approvals: Recording | Holiday BLR | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev
| 26C NF | 26C NF | 26C NF VT- Testing Agent Studio Labs (26C) | 26C NF AI Agent Studio What's new video recording | HOLD eOPN Partner Event (Ruchika POC) 26C NF | Re-do AI Agents/Studio in Using GHR | Retrofit: AI Agents/Studio in Using GHR: Record | Oracle Fusion Cloud HCM: Workflows and Approvals: DD Fixes | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev Fixes | Oracle Fusion Cloud HCM: Workflows and Approvals: Recording | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: DD | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev
| Portfolio Review Prep | 26C NF | 26C NF VT- Testing Agent Studio Labs (26C) | 26C NF | Navigator July Release 26C NF | Re-do AI Agents/Studio in Using GHR | OPN Partner Session: Designing and Managing Workforce and Enterprise Structures in Global Human Resources | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev Fixes | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: DD | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: DD Fixes | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev
| 26C NF | 26C NF Live Session | VT- Testing Agent Studio Labs (26C) AI Agent Studio What's new video recording | OOO | Navigator July Release | OPN Partner Session Prep | Retrofit: AI Agents/Studio in Using GHR: Record | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev | Oracle Fusion Cloud HCM: Workflows and Approvals: Recording | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: DD | 26D BOM Update | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev
| 26C NF | VT- Testing Agent Studio Labs (26C) | AI Agent Studio What's new video recording | OOO | Navigator July Release | OPN Partner Session Prep | Oracle Fusion Cloud HCM: Workflows and Approvals: DD | Oracle Fusion Cloud HCM: Workflows and Approvals: Content Dev | Oracle Fusion Cloud HCM: Workflows and Approvals: Recording | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: DD | 26D BOM Update | Oracle Fusion Cloud HCM Configure Enterprise and Workforce Structures: Content Dev | Holiday BLR
Note on I3: Need some gap to have production services done on PPTs.

## ERP
| 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
CDL | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02
Pankaj | 26C NF | 26C NF | Agentic Apps Partner Training - Testing of Hand on Labs (COE Work) + 26C NFs Unboxing Recording | ERP Process Essentials Gap Analysis | ERP Process Essentials Uplift | Advanced Tax Implementation: DD | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev |  | Holiday BLR
| 26C NF | 26C NF | LIVE SESSION PREP | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 | ERP Process Essentials Uplift | Advanced Tax Implementation: DD | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev
| 26C NF | 26C NFs (AI Agents) | Live Session | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 |  | Advanced Tax Implementation: DD | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev
| 26C NF | 26C NF | Agentic Apps Partner Training - Testing of Hand on Labs (COE Work) | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 |  |  | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev |  | 26D BOM Update
| 26C NF | 26C NF | Agentic Apps Partner Training - Testing of Hand on Labs (COE Work) | ERP Process Essentials Uplift |  |  | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev | Advanced Tax Implementation: Content Dev |  | 26D BOM Update |  | Holiday BLR
Deepak | 2026-07-06: 26B Accounting Hub Event Model Major Change - Content Creation; 2026-07-13: 26C NF; 2026-07-20: 26C NF; 2026-07-27: 26B Accounting Hub Event Model Major Change - Recording OOO; 2026-08-03: Navigator July Release; 2026-08-10: ERP Process Essentials Uplift; 2026-08-17: Partner Session Prep
| 26B Accounting Hub Event Model Major Change - Content Creation | 26C NF | 26C NF | 26B Accounting Hub Event Model Major Change - Recording OOO | 26B Accounting Hub Event Model Major Change - Recording | ERP Process Essentials Uplift | Partner Session Delivery
| 26B Accounting Hub Event Model Major Change - Content Creation | 26C NF | 26C NF | 26B Accounting Hub Event Model Major Change - Recording OOO | 26B Accounting Hub Event Model Major Change - Recording | ERP Process Essentials Uplift | Live Session - Aug 19
| 26B Accounting Hub Event Model Major Change - Content Creation | 26C NF | 26C NF | 26B Accounting Hub Event Model Major Change - Recording OOO | 26B Accounting Hub Event Model Major Change - Recording | ERP Process Essentials Uplift |  |  |  |  | 26D BOM Update
| 26C NF | 26C NF | 26C NF | Navigator July Release OOO | 26B Accounting Hub Event Model Major Change - Recording | Partner Session Prep |  | Holiday DEL | Holiday DEL |  | 26D BOM Update |  | Holiday DEL
Marcelina | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: Compliance Training Portfolio Review for Timelines; 2026-07-27: 26C Payables Implementation - create DD, finalize scope, demo feasibility and environment dependencies; 2026-08-03: 26C Payables Implementation -content development (PPT+AG+T2S Script); 2026-08-10: 26C Payables Implementation -content development (PPT+AG+T2S Script); 2026-09-07: Holiday US
| 26C NF | 26C NF | Compliance Training 26C NF | 26C Payables Implementation - create DD, finalize scope, demo feasibility and environment dependencies | Live Session - Aug 4 | 26C Payables Implementation -content development (PPT+AG+T2S Script)
| 26C NF | 26C NF | ERP Process Essentials Uplift Financials Overview VT Testing | 26C Payables Implementation - create DD, finalize scope, demo feasibility and environment dependencies | 26C Payables Implementation -content development (PPT+AG+T2S Script) | 26C Payables Implementation -content development (PPT+AG+T2S Script)
| 26C NF | ERP Process Essentials Gap Analysis | Live Session Prep | 26C Payables Implementation - create DD, finalize scope, demo feasibility and environment dependencies | 26C Payables Implementation -content development (PPT+AG+T2S Script) | 26C Payables Implementation -content development (PPT+AG+T2S Script) |  |  |  |  | 26D BOM Update
| 26C NF | ERP Process Essentials Gap Analysis | 26C Payables Implementation - create DD, finalize scope, demo feasibility and environment dependencies | 26C Payables Implementation -content development (PPT+AG+T2S Script) | 26C Payables Implementation -content development (PPT+AG+T2S Script) | 26C Payables Implementation -content development (PPT+AG+T2S Script) |  |  |  |  | 26D BOM Update
Chris | 2026-07-06: Common Features Course Recording; 2026-07-13: Partner Session Prep; 2026-07-20: 26C NF; 2026-07-27: Common Features Course Recording; 2026-08-03: 2 NF on D02 Pod Dependency; 2026-08-31: Holiday UK
| Common Features Course Recording | Partner Session Delivery | 26C NF | Common Features Course Recording | 2 NF on D02 Pod Dependency
| Partner Session Prep | Curriculum Audit FY27 Redo | 26C NF | Common Features Course Recording | 2 NF on D02 Pod Dependency | [5 empty] | 26D BOM Update
| Live Session - July 9 | Common Features Course Recording | OOO |  | 2 NF on D02 Pod Dependency | [5 empty] | 26D BOM Update
| OOO | OOO | 26C NF | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO | OOO
Richard | 2026-07-06: 26C NF; 2026-07-13: OOO; 2026-07-20: Testing the Labs for AI Agent Studio 26C Workshop; 2026-07-27: Financial Reporting Content Recording; 2026-08-03: Partner Session Prep; 2026-09-07: Holiday US
| 26C NF | OOO | Testing the Labs for AI Agent Studio 26C Workshop | Financial Reporting Content Recording | Partner Session Delivery
| JVM AG Content Update/Record | OOO | Testing the Labs for AI Agent Studio 26C Workshop | Financial Reporting Content Recording | JVM AG Content Update/Record
| 26C NF | OOO | Testing the Labs for AI Agent Studio 26C Workshop | Financial Reporting Content Recording | JVM AG Content Update/Record | [5 empty] | 26D BOM Update
| 26C NF | OOO | 26C NFs JVM Feature dependent on PM data seeding | Partner Session Prep | JVM AG Content Update/Record | [5 empty] | 26D BOM Update
Barney | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: Curriculum Audit FY27 Redo; 2026-07-27: Curriculum Audit FY27 Redo; 2026-08-03: 26B Applied Learning Accounting Hub Major Uplift Çontent Creation; 2026-08-31: Holiday UK
| 26C NF | 26C NF | Curriculum Audit FY27 Redo | 26B Applied Learning Accounting Hub Major Uplift Çontent Creation
| 26C NF | 26C NF | Curriculum Audit FY27 Redo | 26B Applied Learning Accounting Hub Major Uplift Çontent Creation
| 26C NF | 26C NF | Curriculum Audit FY27 Redo | 26B Applied Learning Accounting Hub Major Uplift Çontent Creation | [6 empty] | 26D BOM Update
| 26C NF | 26C NF | Curriculum Audit FY27 Redo | 26B Applied Learning Accounting Hub Major Uplift Çontent Creation | [6 empty] | 26D BOM Update
Note on D27: Issue faced. Unable to create content.

## SCM
| 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
CDL | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02
David | 2026-07-06: Two AI Agents from D2 Pod; 2026-07-13: 26C NF; 2026-07-20: 26C NF; 2026-07-27: 26C NF; 2026-09-07: Holiday US | Nav additional time and extra days
| Two AI Agents from D2 Pod | 26C NF | 26C NF | 26C NF
| Live Session - Jul 8 | 26C NF | 26C NF | Navigator July Release
| 26C NF | Curriculum Audit Report/Changes | 26C NF | Manufacturing Foundation Course Uplift with 26B NFs & AI - Design Doc | [6 empty] | 26D BOM Update
| Curriculum Audit Report/Changes | Curriculum Audit Report/Changes | OOO | Manufacturing Foundation Course Uplift with 26B NFs & AI - Content Creation | [6 empty] | 26D BOM Update
Nick | 2026-07-06: 26C NF; 2026-07-13: SCM Masterclass - Coverage of Additional Topics; 2026-07-20: Partner Session Prep Testing Agent Studio OU Course Labs; 2026-07-27: AI Agent Studio - Agentic Apps Virtual Workship July 28-30 Travel; 2026-08-03: 26C NF; 2026-09-07: Holiday US
| 26C NF | SCM Masterclass - Coverage of Additional Topics | OPN Partner Session Delivery | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 | 26C NF | Grab Taxi Customer Specific Live Session - Aug 11
| 26C NF | SCM Masterclass - Coverage of Additional Topics | Testing the Labs for AI Agent Studio 26C Workshop | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 | 26C NF
| 26C NF | Testing the Labs for AI Agent Studio 26C Workshop | Testing the Labs for AI Agent Studio 26C Workshop | AI Agent Studio - Agentic Apps Virtual Workship July 28-30 | Master cert exam dry run- AI Agents Developer Course |  | Live Session - Aug 20 |  |  |  | 26D BOM Update
| 26C NF / Curriculum Audit Report/Changes | Partner Session Prep Testing Agent Studio OU Course Labs | Navigator July Release | 26C NF | [6 empty] | 26D BOM Update
Farrell | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: 26C NF; 2026-07-27: 26C NF; 2026-08-03: Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation; 2026-09-07: Holiday US
| 26C NF | Live Session - Jul 14 | 26C NF | 26C NF | Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation | Partner Session Prep
| Curriculum Audit Report/Changes | CTO VT Changes | 26C NF | Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation | Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation | Partner Session Prep
| 26C NF | Adv Supply Chain VT Changes | 26C NF | Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation |  | Partner Session Delivery |  |  |  |  | 26D BOM Update
| 26C NF | Adv Supply Chain VT Changes | 26C NF | Order Mgmt Course Uplift 25D-26B, Agents, Backlog Mgmt - Content Creation | [6 empty] | 26D BOM Update
Kirthika | 2026-07-06: 26C NF; 2026-07-13: 26C NF; 2026-07-20: 26C NF VT- Testing Agent Studio Labs (26C); 2026-07-27: 26C NF; 2026-09-14: Holiday CHE
| 26C NF | 26C NF | 26C NF VT- Testing Agent Studio Labs (26C) | 26C NF VT – Oracle SCM Cloud Demand Planning Implementation
| 26C NF | 26C NF | 26C NF | 26C NF
| 26C NF | 26C NF | 26C NF | 26C NF | [6 empty] | 26D BOM Update
| 26C NF | 26C NF VT- Testing Agent Studio Labs (26C) | 26C NF OOO | [7 empty] | 26D BOM Update |  | Holiday CHE
Ashik | OOO | 26C NF | 26C NF Partner Session Prep | 26C NF | 26C NF | Navigator July Release 1Z0-1065-26: Procurement HPE Question Review (Half Day) | Content Dev: PRC: 25B - 26B +AI: DD | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Holiday BLR | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI
| OOO | 26C NF | VT- Testing Agent Studio Labs (26C) | 26C NF Live Session Prep (Half Day) | 26C NF | Navigator July Release | Content Dev: PRC: 25B - 26B +AI: DD | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI
| 26B 5 AI Agents from D2 Pod | 26C NF | VT- Testing Agent Studio Labs (26C) | Live Session - Jul 29 26C NF | 26C NF | Navigator July Release | Content Dev: PRC: 25B - 26B +AI: DD | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI
| Portfolio Review Prep | Partner Session Prep | Partner Session: AI Agentic App: Sourcing Command Center | 26C NF | Master cert exam dry run- AI Agents Developer Course (Half Day) 26C NFs | Deloitte Partner session for Agentic Apps- Prep | Deloitte Partner session for Agentic Apps- Prep+Session- APAC | Live Session - Aug 27 | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | 26D BOM Update | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI
| 26C NF | Partner Session Prep VT- Testing Agent Studio Labs (26C) | 26C NF | 26C NF | 26C NF | Deloitte Partner session for Agentic Apps- Prep | Deloitte Partner session for Agentic Apps- Prep+Session- NAMER | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | Content Dev: PRC: 25B - 26B +AI | 26D BOM Update | Content Dev: PRC: 25B - 26B +AI | Holiday BLR
Omkar | Content Dev: Cost Management Implementation (24D to 26B, AI) | 26C NF | Content Dev/Recording 26C NFs (Half Day) VT- Testing Agent Studio Labs (26C) (Half Day) | Content Dev: Cost Management Implementation (24D to 26B, AI) | Content Dev FIXES: Cost Management Implementation (24D to 26B, AI) | Deloitte Partner session for Agentic Apps- Prep | Deloitte Partner session for Agentic Apps- Prep+Session- APAC | Recording: Cost Management Implementation (24D to 26B, AI) (Including Retrofitting 26B AI Agents Demo to 26C | OOO | Oracle Warehouse Management System Cloud Deep Dive: DD | Holiday BLR | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev
| 26C NF / WMS VT (Half Day) | 26C NF | Content Dev/Recording 26C NFs- Unboxing (Half Day) WMS VT (Half Day) | Content Dev: Cost Management Implementation (24D to 26B, AI) | Content Dev FIXES: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) (Including Retrofitting 26B AI Agents Demo to 26C | OOO | Oracle Warehouse Management System Cloud Deep Dive: DD | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev
| 26C NF | 26C NF | Content Dev: Cost Management Implementation (24D to 26B, AI) | 26C NF AI Agents - 3 Agents | Deloitte Partner session for Agentic Apps- Prep (Half Day) Content Dev FIXES: Cost Management Implementation (24D to 26B, AI) (Half Day) | Recording: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) | Live Session - Aug 26 | OOO | Oracle Warehouse Management System Cloud Deep Dive: DD | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev
| 26C NF | 26C NF | Content Dev: Cost Management Implementation (24D to 26B, AI) | 26C NF AI Agents - 3 Agents | Master cert exam dry run- AI Agents Developer Course (Half Day) Deloitte Partner session for Agentic Apps- Prep (Half Day) | Recording: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) (Including Retrofitting 26B AI Agents Demo to 26C | Recording: Cost Management Implementation (24D to 26B, AI) (Including Retrofitting 26B AI Agents Demo to 26C | OOO | OPN Partner Session Prep | OPN Partner Session Delivery | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev
| 26C NF | Content Dev/Recording 26C NFs (Half Day) VT- Testing Agent Studio Labs (26C) (Half Day) | Content Dev: Cost Management Implementation (24D to 26B, AI) | 26C NF AI Agents - 3 Agents | Deloitte Partner session for Agentic Apps- Prep | Recording: Cost Management Implementation (24D to 26B, AI) | Recording: Cost Management Implementation (24D to 26B, AI) (Including Retrofitting 26B AI Agents Demo to 26C | Deloitte Partner session for Agentic Apps- Prep+Session- NAMER | OOO | OPN Partner Session Prep | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Oracle Warehouse Management System Cloud Deep Dive: Content Dev | Holiday BLR
Note on B4: 1 completed. 1 has SR, awaiting resolution. Added to the AI-Agent tracking list by OUPM.
Note on E4: 2/7 done. 5 still pending.
Note on D12: CDL requested more time. Timeline yet to be confirmed to OUPM as on 27-Jul.
Note on E14: 3/34 complete.
Note on E20: 18/35 completed.
Note on B25: 4 complete. 1 remaining.
Note on E25: 9/31 complete

## CX
| 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
CDL | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02
Phil | 26C NF | 26C NF | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl | Skills Check Dev: Fusion Service Impl |  | Holiday UK
| 26C NF | 26C NF | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl | Cert Question Updates: 2-3 questions for Fusion Impl Pro
| 26C NF | 26C NF | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl |  |  |  |  | 26D BOM Update
| Portfolio Meeting Prep Day | Portfolio Meeting Prep Day | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl (Content Dev) | AG Dev: Fusion Service Impl |  |  |  |  | 26D BOM Update
| Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours | Flexible Hours
Shivam | 26C NF | 26C NF | 26C NF | Content Dev: Oracle CPQ Cloud : Site Administration | Content Dev: Oracle CPQ Cloud : Site Administration | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Site Administration: Recording | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Pricing: Content Dev | Holiday BLR | OPN Partner Session Prep | Oracle CPQ Cloud : Commerce: Content Dev
| 26C NF | 26C NF | 26C NF | Content Dev: Oracle CPQ Cloud : Site Administration | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Site Administration: Recording | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Configuration: Recording | Oracle CPQ Cloud : Configuration: Recording | Oracle CPQ Cloud : Commerce: Content Dev
| 26C NF | 26C NF | 26C NF | Content Dev: Oracle CPQ Cloud : Site Administration | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Site Administration: Recording | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Pricing: Content Dev | 26D BOM Update | Oracle CPQ Cloud : Configuration: Recording | Oracle CPQ Cloud : Commerce: Content Dev
| 26C NF | Portfolio Meeting Prep Day | Content Dev: Oracle CPQ Cloud : Site Administration | Content Dev: Oracle CPQ Cloud : Site Administration | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Site Administration: Recording | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Pricing: Content Dev | 26D BOM Update | HOLD eOPN Partner Event (Ruchika POC) | Oracle CPQ Cloud : Commerce: Content Dev
| 26C NF | 26C NF | Content Dev: Oracle CPQ Cloud : Site Administration | Content Dev: Oracle CPQ Cloud : Site Administration | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Configuration: Content Dev | Oracle CPQ Cloud : Site Administration: Recording | Oracle CPQ Cloud : Pricing: Content Dev | Oracle CPQ Cloud : Pricing: Content Dev | OPN Partner Session Prep | Oracle CPQ Cloud : Configuration: Recording | Holiday BLR

## EPM
| 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
CDL | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02
Akash | 2026-07-06: Admin Planning Modules AG Content Dev; 2026-07-13: Admin Planning Modules AG Content Dev; 2026-07-20: Admin Planning Modules AG Content DEV + PPT Fixes + Recording Ag2 for Demo; 2026-07-27: Admin Planning Modules Recording; 2026-08-03: AI Agents in EPM; 2026-09-14: Holiday BLR
| Admin Planning Modules AG Content Dev | Admin Planning Modules AG Content Dev | Admin Planning Modules AG Content DEV + PPT Fixes + Recording Ag2 for Demo | Admin Planning Modules Recording | Predictive Cash Forecasting
| Admin Planning Modules AG Content Dev | EPM Portfolio Review Meeting Prep | Admin Planning Modules AG Content DEV + PPT Fixes + Recording Ag2 for Demo | Admin Planning Modules Recording (Half Day) **Customer Query - 260725-000083 (Half Day)??? | EPCM
| Admin Planning Modules AG Content Dev | Admin Planning Modules AG Content Dev OOO (Sick Leave) | Live Session - EPM - Jul 23 | Admin Planning Modules Case Study
| Admin Planning Modules AG Content Dev | Admin Planning Modules Case Study OOO (Sick Leave) | Admin Planning Modules Recording | Admin Planning Modules Case Study | [8 empty] | Holiday BLR

## Portfolio Analysis Tracking
Portfolio Activity
Pillar | CDL | Portfolio Mtg Date / Status | OUPM : Disptach | Schedule from DM
CX | Shivam | 2026-07-29
CX | Phil | 2026-07-28 | 2026-07-28
EPM | Akash | 2026-07-30
ERP | Pankaj | Complete | 2026-07-13 | Received
ERP | Deepak | 2026-07-14 | 2026-07-27
ERP | Marcelina | Complete | 2026-07-15 | To Be Received
ERP | Richard | 2026-07-10 | 2026-07-27
ERP | Chris | 2026-07-21 | 2026-07-27
ERP | Barney | 2026-07-22 | 2026-07-27
HCM | Sarah | 2026-07-15 | 2026-07-20 | Received
HCM | Deb | Complete | 2026-07-20 | Received
HCM | Jess | 2026-07-22 | 2026-07-22 | To Be Received
HCM | Nigel | 2026-07-22 | 2026-07-22 | Received
HCM | Kurt | 2026-07-23 | 2026-07-23 | To Be Received
HCM | Rohit | 2026-07-20 | 2026-07-20 | Received
SCM | Farrell | Complete | 2026-07-16 | To Be Received
SCM | Kirthika | Complete | 2026-07-20 | To Be Received
SCM | Omkar | Complete | 2026-07-13 | Received
SCM | David | 2026-07-17 | 2026-07-20 | To Be Received
SCM | Nick | 2026-07-17 | 2026-07-20 | To Be Received
SCM | Ashik | Complete | 2026-07-27 | Received

## CDL Comparison Config
Activity aliases |  | Comparison settings
Standard activity | Accepted variation | Setting | Suggested value
New Feature | NF | Comparison period | Current sprint + next 2 sprints
New Feature | New Features | Person matching | Exact, ignoring capitalization/spaces
Content Development | Content Dev | Date matching | Same sprint/week
Content Development | Content Creation | Activity matching | Alias + keyword-based
Design Document | Design Doc | Auto-update workbook | No
Recording | Course Recording | Notify about additions | Yes
|  | Notify about removals | Yes
|  | Notify about rewording only | Review
|  | Output location | Proposed Changes sheet

## Comparison_Data
Source | CDL_Name | Week_Start | Original_Activity | Standard_Activity | Mapping_Status | Match_Key | Comparison_Result